Botany Conference Board Report - March 2024

Core Planning Committee meeting, Jan. 19, 2024

- Presidents and/or Program Directors from BSA, ASPT, SHC, AFS, SEB (IAPT via emails)

- Reviewed Fiscal Projection Spreadsheet

  - Registration rates were increased and are here.

  - All partners are urged to help improve the financial bottom line:

    - promote the conference to increase attendance

    - identify potential exhibitors / sponsors and send contact info to Johanne

- Discussed two potential sites for Botany 2026 (Omaha versus Syracuse)

  - Omaha was preferred based on numerous criteria, most persuasively:

    - Convenience of having entire conference within a single venue (Syracuse would have required a five-minute walk between two venues)

    - Generous room block for students at significantly reduced rates

  - Omaha was selected as site for Botany 2026 with full support of committee

- Future fully-virtual?

  - Poll attendees during Botany 2024 post-conference survey to gauge interest

  - No appetite for a hybrid conference (substantial financial loss)

Conference Status, as of Feb. 28, 2024

- Abstract submission site – Opened on February 1st for submissions…Currently 53 abstracts submitted.  Created a way to view submitted abstracts….a searchable pdf.

- Registration Site also opened on Feb 1.  184 people registered.

  - Soon, Johanne will send out a complimentary registration code and hotel information (waiting for confirmation numbers).

- Symposia and Colloquia are posted on the Conference Website

- Workshops were reviewed and accepted by committee of participating society representatives.  Workshops are on the website.

- About 10 Field trips are included this year. This has been a real challenge – awaiting final pricing on buses and then field trip information will be posted and added to the reg site.  We will make a major push for signing up for these once they are added to the reg site.  Possibly having a special field trip for PLANTS students

- This year’s Featured Speakers giving special lectures will be:

  - Plenary Address – Colin Khoury

  - Annals of Botany Lecture - Kathleen Kay

  - Emerging Leader Lecture -  Joyce Gloria Onyenedum

  - Address of the BSA President-Elect – Jenny Xiang

  - Belonging in Botany – Will be a panel – waiting for names

  - Kaplan Memorial Lecture – Cindy Jones

  - Regional Botany Special Lecture - Kaya DeerInWater

  - Address of ASPT Pres Elect – Dave Tank

  - Distinguished Ethnobotanist Speaker – Mark Merlin

- The Future – Botany 2026 – Omaha NE.  Will have more information soon

Submitted by:

Johanne and Melanie